## الورقة1
Goals | Work package | Activitiy List | Duration | Responsible | Support & consultant | Outcome | KPI | Cost
Grow and diversify our funding base | Secure diversified funding through State and Federal government departments | Build a profile file for the organization | 1 month | Marketing officer | Communication or marketing Director | Orgnazitional Profile | nothing | 0$
|  | Build Pitch Deck for the Government | 1 month | Marketing officer | Communication or marketing Director | Pitch Deck to request the government for funding | nothing | 0$
|  | Collect the data for the Government | 3 months | lead generation officer | Communication or marketing Director | Goverments data (Inculding their contact information) | Numbers of the international Goverments that can help | 0$
|  | Call the Government | 6 months | PR officer | Communication or PR Director | nothing | Numbers for the total governments call, and Numbers for the active calls | 0$
|  | Send the funding request file | 6 months | PR officer | Communication or PR Director | nothing | Numbers of the sent emails and for the active sending | 0$
|  | Setup meeting to present the request | 1 year | PR Representative | PR Director | nothing | Numbers of Governments that we meet with them | 0$
|  | Follow up (after they receive the file and meeting - and through these steps) | 1 year | PR officer | PR Director | nothing | Numbers of a follow ups | 0$
|  | Keep socialling | all the time | Social Media officer | Communication or marketing Director | present about the org | No of Presenten our org, and through what? | 0$
|  | Research and compile a list of at least 50 State and Federal government grants. | 2 months | Marketing and Fundraising Manager | Development Director | Create database of at least 50 State and Federal government grants | Number of State and Federal government grants in database | $50 to purchase Funds for NGOs yearly Premium database
[6 empty] | Raise a minimum of $80,000 (Year 1) | Amount raised in comparison to funding target
|  | Draft and Send out 50 State and Federal government proposals. | 10 months | Programme Director | Development Director | Prepare State and Federal government proposals | Number of State and Federal Government proposal sent | 0$
| Secure foundation funding and INGO contract | Build a profile file for the org | 1 month | Marketing officer | Communication or marketing Director | Orgnazitional Profile | nothing | 0$
|  | Build a file for INGO to ask for funding to the org, like the pitch deck | 1 month | Marketing officer | Communication or marketing Director | Pitch Deck for requesting INGO for funding | nothing | 0$
|  | Collect the data for the INGO, with the contact information | 3 months | lead generation officer | Communication or marketing Director | INGO data (Including their contact information) | Numbers of the INGO that can help | 0$
|  | Call the INGO | 6 months | PR officer | Communication or PR Director | nothing | Numbers for the INGO that we called, and Numbers for the active calls | 0$
|  | Send the funding request file | 6 months | PR officer | Communication or PR Director | nothing | Numbers of the sent emails and for the active sending | 0$
|  | Setup meeting to present the request | 1 year | PR Representative | PR Director | nothing | Numbers of INGO the we meet with them | 0$
|  | Follow up (after they recieve the file and meeting - and through these steps) | 1 year | PR officer | PR Director | nothing | Numbers of a follow ups | 0$
|  | Keep socialling (through the social media and events) | all the time | Social Media officer | Communication or marketing Director | present about the organization | No of Presenten our org, and through what? | 0$
|  | Research and compile a list of at least 50 foundation grants and INGO contract | 6 months | Marketing and Fundraising Manager | Development Director | Create database of at least 50 foundation grants and INGO contract | Number of foundation grants and INGO contract in database | This activity will incur zero added cost
[6 empty] | Raise a minimum of $50,000 (Year 1) | Amount raised in comparison to funding target
|  | Draft and Send out 50 foundation and INGO contract proposals | 6 months | Programme Director | Development Director | Prepare foundation and INGO contract proposals | Number of foundation and INGO contract proposal sent | This activity will incur zero added cost
| Increase Individual giving | Build a profile file for the organization | 1 month | Marketing officer | Communication or marketing Director | Orgnazitional Profile | nothing | 0$
|  | Build a file for Partners to ask for funding to the org, like the pitch deck | 1 month | Marketing officer | Communication or marketing Director | Pitch Deck to request Partners for funding or to be partner | nothing | 0$
|  | Collect the data for the companies, with the contact information | 3 months | lead generation officer | Communication or marketing Director | Companies data (including their contact information) | Numbers for the Companies on the world that can help | 0$
|  | Call the companies | 6 months | PR officer | Communication or PR Director | nothing | Numbers for the Companies that we called, and Numbers for the active calls | 0$
|  | Send the funding request file | 6 months | PR officer | Communication or PR Director | nothing | Numbers of the sent emails and for the active sending | 0$
|  | Setup meeting to present the request | 1 year | PR Representative | PR Director | nothing | Numbers of companies that we meet with them | 0$
|  | Follow up (after they recieve the file and meeting - and through these steps) | 1 year | PR officer | PR Director | nothing | Numbers of a follow ups | 0$
|  | Keep socialling (through the social media and event) | all the time | Social Media officer | Communication or marketing Director | present about the organization | No of Presenten our org, and through what? | 0$
|  | Research and compile a list of at least 50 Individual donors | Two months | Programme Director/Communication cordinator | Development director | Send and write emails for donors to call for donations. | Estimated number of the donors that were reached out. | 0$
|  | Develop an e-mail marketing campaign targeting individuals to make small donations in the amounts of $50, $100, $250, $500 and offer the option to make an in-kind donation, including new or used tech material. | two weeks | Email Marketing specialist | Manager/ Writer | Design compelling emails with a powerful message content for the campaign | Number of the replies from the emails that were sent. OR, Amount raised from the donors after the campaign | 0$
|  | Develop systems to analyze response rate, amounts donated and establish a system to categorize and create value for the donors by advertising donors on our website. Example; featuring individual donors on the website. | 2 months | Marketing and Fundraising Manager | Development Director | Create database of at least 100 donors | Number of donors in database | $50
| Secure corporate (CSR)funding | Build a profile file for the organization | 1 month | Marketing officer | Communication or marketing Director | Orgnazitional Profile | nothing | 0$
|  | Build a file for companies to ask for funding for the organization, like the pitch deck | 1 month | Marketing officer | Communication or marketing Director | Pitch Deck for requesting the Companies for funding | nothing | 0$
|  | Collect the data for the companies, with the contact information | 3 months | lead generation officer | Communication or marketing Director | Companies data ( includs their contact info) | Numbers for the Companies on the world that can help | 0$
|  | Call the companies | 6 months | PR officer | Communication or PR Director | nothing | Numbers for the Companies that we called, and Numbers for the active calls | 0$
|  | Send the funding request file | 6 months | PR officer | Communication or PR Director | nothing | Numbers of the sent emails and for the active sending | 0$
|  | Setup meeting to present the request | 1 year | PR Representative | PR Director | nothing | Numbers of companies that we meet with them | 0$
|  | Follow up (after they recieve the file and meeting - and through these steps) | 1 year | PR officer | PR Director | nothing | Numbers of a follow ups | 0$
|  | Keep socialling (through the social media and event) | all the time | Social Media officer | Communication or marketing Director | present about the org | No of Presenten our org, and through what? | 0$
|  | Research and compile a list of at least 50 corporate (CSR) grants | 3 month | Marketing and Fundraising Manager | Development Director | Create database of at least 50 corporate (CSR) grants | Number of contract corporate (CSR) grants in database | 0$
|  | Draft 50 corporate (CSR) sponsorship letters/applications | 6 months | Programme Director | Development Director | Prepare (CSR) sponsorship letters/applications | Number of(CSR) sponsorship letters/applications sent | 0$
|  | Reach out and send marketing ad to the identified companies and ask for small donations in the amounts of $1,000 to $5,000 and offer the option to make an in-kind donation, including new or used tech material | 5 Months | Programme Director | Development Director | Having a list of the corporation companies. | Number of the donation raised from the companies. | 0$
| Increase revenues from services and products | Develop income generating model for our Projects | 3 month | Finacical Manager | CFO | model income generating plan for Projects | Estimated revenue growth | 0$
| Develop Internal Cost Controls to tight management of financial resources | Develop strong Financial Management system for funds raised | 3 months | Marketing and Fundraising Manager | Development Director | Create a system with new features | Number funds raised in system | 50 $
Strengthen our Internal staff /team and governance capacity | Board Involvement and motivation | 1-Send weekly emails with any updates. 2-Set program that requires the attendance of the board, this can happen by making one member to lead the program alone to involve them. | Monthly | Manager | Development Director | Monitoring visits for projects Monthly by different Directors from the board. | Tracking the performance to assess the result, with considering achieveing the goals set by the organization. | 0$
| Develop the Board to meet the governance needs and requirements of the future | 1-Schedule more frequent meetings between the members, this is to ensure the objectives of the organization are met. Also, determine the abilities of the board and ensure that the skills are applied for the future work. | Every 3 months | The chair of the Board | Manager | Participate in group discussions to reflect on the performance and to see what is lacking. | Number of the group disccussions that allow for feedback and the outcome from it | 0$
| Acquire the necessary staff and leadership competencies to achieve organizational goals | Recruit high caliber of local personnel’s to coordinate and manage in-country operations | 3 months | Recruiter - HR | Human resources | Build a strong organization team that can move the org forward | Number of new high caliber | 0$
|  | Develop Volunteer program to recruit international and local volunteers with financial and in-kind incentives integrated to attract high value personnel | 1 month | HR | HR | create an annual program for international volunteers | Number of new international volunteers and local volunteers | 0$
| Developed management culture to promote innovation and organizational learning. | Build Administrative Policies and Procedures Manual | 1 weeks | Culture & Engagement organizational | Human resoursec | create part of HR strategy that includes all the details about the organization's culture | nothing | 0$
Focus and strengthen our program direction | Strengthen AIR’s effectiveness to impact selected community-focused initiatives | 1-Research project in the internal operations of the team to spot the weak points. 2-Develop an evaluation plan for certain initiatives to ensure the impact is achievable by the workers. 3-Set an action plan for specific goals with deadlines to focus on community improving. | 4 months | Programme Director | Development Director | Presentation of the findings, set priorities mission to develop the team's abilities for the selected areas. | The overall performance of AIR and the number of successful goals of the organization | 0$
| Strengthen and expand collective action and learning among beneficiary communities | 1-Implement plans to concentrate on the education and information resources, to connect the beneficiary community with knowledge needed for development. 2-Increase the surveying method to track people's learning in the target community. | 3 months | Programme Director or Researcher | Development Director | Having strategies on how to engage people and make them more productive. Also the result from the survey will be very helpful. | Total number of the plans and the surveying mtethods | 0$
| Create systems and processes to effectively disseminate AIR impact | Quantitative measurement: using numerical data (performance measures, indicators, etc.) to measure whether things are getting better or worse | 6 months | Programme Director | Development Director | Set a digital system to measure impact | The system that helped to identify the most impactful projects | 20$
Grow and improve our reputation and stakeholder engagement | Build our profile/ brand as an effective and preferred ICT 4 development partner in Ghana | Developing the Brand Identity and pitch deck , Redesign a logo that contains values | 3 month | Marketing and Fundraising Manager | Development Director | create new pitch deck & brand book | Estimated number of partner that were register with us . | 20$
| increasing Value-added to Customers | Creating insightful content including how-to tutorials, Q&A live videos, email newsletters, infographics and blog posts | 1 month | Marketing and Fundraising Manager | Development Director | creating insightful content | The number of users who viewed this content | 0$
| Implement a communications strategy in support of program priorities and initiatives | Make small events to introduce people with AIR's programs and Initiatives. | 3 Months | Marketing/ Communication manager | Programme Director | The recognition of AIR will expand | Number of new partners and volunteers | Maybe 100$
|  | Increase interaction with the community through social media | 1 month | Communication cordinator | Development Director | Increase content in social meadia | Number of followers | 0$
| Improve transparency and accountability to donors and the community by reporting on the impact of all programs. | Send a monthly email for (our news) | all the time | Marketing Officer | Communication or marketing Director | Inform our people about us and about our news | Number of the sent emails and active sending | 0$
|  | Activate the social media account | all the time | Social Media Officer | Marketing Director | Build a social media account to comunicate with the org and send our news | Number of veiwers and actives users | 0$
Improve operational effectiveness and risk mitigation | Monitor and evaluate performance of all programs using technology to improve data collection, aggregation and analysis. | Collect the data of the programs | 2 days | Project Management Associate | PMO Director | Data of the programs | nothing | 0$
|  | Make a Q&A and fill it after each program | 4 days | Project Management Associate | PMO Director | result for the program | nothing | 0$
|  | Send survey or send someone to ask the people about the program and see the affective about it | 4 days | Project Management Associate | PMO Director | Result of the impact of our programs | Number for the positive effect and the total effectiveness from each program participants | 0$
|  | Save the data | 1 hour | Archiver or Project Management Associate | PMO Director | Program result and details data | nothing | 0$
| (for the HR)Organizational systems and procedures (documentation, electronic archiving, sharing, horizontal learning etc) developed and/or updated | Build data center | 2 months | IT officer | IT or Technology Director | Data center that includes all the companies result and volunteers with employees | nothing | 100$ to 50k$ Depens on the system
|  | Save & collect data | all the time | Archiver , HR officer | HR | Data for every employee or volunteer information with our organization | nothing | 0$
| Develop reporting systems for impact of programs. | Anylazing data to improve the impact of the program | 1 week | Data analyst | data center, IT | Reports of each programs | nothing | 0$